## Content
Content
1. Efforts and costs
2. Processing
2.1 Breakdown structure of sampling time estimates
2.1 Breakdown structure of drone-data collection time estimates
2.3 Breakdown structure of data processing and analysis time estimates
Overview
The following tables give an overview of labour time and associated cost estimates. The cost estimates are specifically for the oil/gas/mining sector in Alberta, Canada.
We compare two approaches for acquiring information on regeneration success, including a drone-assisted and field-sampling only approach.
In the drone-assisted approach multispectral and RGB imagery is collected at ~3 and ~1.5 cm resolution, respectively.
Furthermore, we have created a third scenario in which the drone-pilot uses more advanced cameras (i.e., higher frame rates and image resolution)
Comments
All costs are provided in $CAD.
Times of field sampling and image collection (current setup) are based on field-measured times.
Drone-assisted approach uses ~5 transects with 10 quadrats each, per 15 ha site. (72 min / transect)
Hypothetical field-only approach uses, ideally, double the amount of transects
Current drone setup includes Phantom 4 RTK (RGB) and RedEdge-MX (multispectral)
Advanced drone setup includes Zenmuse P1 (RGB) and RedEdge-P (multispectral).
Times of the advanced setup are based on estimates derived from MapPilotPro and field-measured contingency times (from current drone setup)
Processing times are balpark estimates.

## 1. Efforts and Costs - Dynamic
Number of site pairs: |  | 1
Number of transects per site pair in "Field-only" scenario: |  | 20
[5 empty] | Drone-assisted scenario |  | Field only scenario | Drone-assisted scenario | Field only scenario | Drone-assisted minus field-only scenario
| Supplementary costs for drone-assisted approach | Hectares ROW sites | Hectares wildfire sites | Total hectares | Image collection days | Sample collection days | Sample collection days | Cost per ha | Cost per ha | Cost per ha
| Current drone setup | 20 | 20 | 40 | 2 | 2 | 2 | 481.6071 | 330.7827 | 150.8244
| Advanced setup | 20 | 20 | 40 | 0.8 | 2 | 4 | 439.25 | 330.7827 | 108.4673
Total "Effort estimate" Drone-assisted approach |  | $ | 19264.2857 |  |  |  |  | Current drone setup |  |  | Total "Effort estimate" Field-only approach |  | $ | 8466.7857 |  |  |  |  | Same number of transects
Regeneration assessment Drone-assisted approach |  | Paired sites are 20 ha (40 total) and include 6 transects (12 total) each | [5 empty] | Rik Nuijten |  |  | Regeneration assessment Field-only approach |  | Paired sites are 20 ha (40 total) and include 6 transects (12 total) each | [5 empty] | Rik Nuijten
[8 empty] | Date 2023-09-25 | [10 empty] | Date 2023-09-25
ID | Project Item/Task Name | Resource Type | Resource Quantity | Rate per Unit | Unit | Estimated Effort Cost (sub total) | Cost by hectare | Remarks |  |  | ID | Project Item/Task Name | Resource Type | Resource Quantity | Rate per Unit | Unit | Estimated Effort Cost (sub total) | Cost by hectare | Remarks
| Data Acquisition |  |  |  |  | 6900 | 172.5 |  |  |  |  | Data Acquisition |  |  |  |  | 4400 | 110
1 | Two field technicians | Labour | 2 | 2200 | Day | 4400 | 110 | Hired for 10 hrs; Minimum of two for safety |  |  | 1 | Two field technicians | Labour | 2 | 2200 | Day | 4400 | 110 | Hired for 10 hrs; Minimum of two for safety
2 | Drone pilot | Labour | 2 | 1250 | Day | 2500 | 62.5 | Hired for 10 hrs / day
[17 empty] | 220 | 5.5
[6 empty] | 440 | 11 |  |  |  | 2 | Field equipment / GNSS / ipad | Equipment | 2 | 110 | Flat rate | 220 | 5.5
3 | Drone equipment | Equipment | 2 | 110 | Flat rate / day | 220 | 5.5
4 | Field equipment / GNSS / ipad | Equipment | 2 | 110 | Flat rate / day | 220 | 5.5 |  |  |  |  | Miscellaneous |  |  |  |  | 2114.2857 | 52.8571
[11 empty] | 3 | Vehicle | Travel | 2 | 150 | Flat rate | 300 | 7.5
| Miscellaneous |  |  |  |  | 3014.2857 | 75.3571 |  |  |  | 4 | Hotel crew | Travel | 2 | 150 | Night | 300 | 7.5 | Shared room for technicians
5 | Vehicle | Travel | 2 | 150 | Flat rate / day | 300 | 7.5 |  |  |  | 5 | Per diem | Travel | 4 | 300 | Day | 1200 | 30
6 | Hotel crew | Travel | 2 | 150 | Night | 300 | 7.5 |  |  |  | 6 | Operating costs of vehicle | Travel | 314.2857 | 1 | Km | 314.2857 | 7.8571 | 1100 km per 7 days (250 km GP-Hotel; 50 km to site)
7 | Hotel pilot | Travel | 2 | 150 | Night | 300 | 7.5 | Shared for technicians; private for pilot
8 | Per diem | Travel | 6 | 300 | Day | 1800 | 45 |  |  |  |  | Processing and Analysis |  |  |  |  | 1732.5 | 43.3125
9 | Operating costs of vehicle | Travel | 314.2857 | 1 | Km | 314.2857 | 7.8571 | 1100 km per 7 days (250 km GP-Hotel; 50 km to site) |  |  | 7 | Data analyst - FIXED | Labour | 1 | 1320 | Day | 1320 | 33 | Hired for 8 hrs / day; 12 hours total.
[11 empty] | 8 | Data analyst - VARIABLE | Labour | 0.3125 | 1320 | Day | 412.5 | 10.3125
| Processing and Analysis |  |  |  |  | 8910 | 222.75
10 | Data analyst - FIXED | Labour | 5.75 | 1320 | Day | 7590 | 189.75 | Hired for 8 hrs / day; 40 hours total.
11 | Data analyst - VARIABLE | Labour | 1 | 1320 | Day | 1320 | 33
[6 empty] | 19264.2857 | 481.6071 | [9 empty] | 8466.7857 | 211.6696
Total "Effort estimate" Drone-assisted approach |  | $ | 17570 |  |  |  |  | Advanced drone setup |  |  | Total "Effort estimate" Field-only approach |  | $ | 13231.3095 |  |  |  |  | Double number of transects
Regeneration assessment Drone-assisted approach |  | Paired sites are 20 ha (40 total) and include 6 transects (12 total) each | [5 empty] | Rik Nuijten |  |  | Regeneration assessment Field-only approach |  | Paired sites are 20 ha (40 total) and include 12 transects (24 total) each | [5 empty] | Rik Nuijten
[8 empty] | Date 2023-09-25 | [10 empty] | Date 2023-09-25
ID | Project Item/Task Name | Resource Type | Resource Quantity | Rate per Unit | Unit | Estimated Effort Cost (sub total) | Cost by hectare | Remarks |  |  | ID | Project Item/Task Name | Resource Type | Resource Quantity | Rate per Unit | Unit | Estimated Effort Cost (sub total) | Cost by hectare | Remarks
| Data Acquisition |  |  |  |  | 5400 | 135 |  |  |  |  | Data Acquisition |  |  |  |  | 7333.3333 | 183.3333
1 | Two field technicians | Labour | 2 | 2200 | Day | 4400 | 110 | Hired for 10 hrs; Minimum of two for safety |  |  | 1 | Two field technicians | Labour | 3.3333 | 2200 | Day | 7333.3333 | 183.3333 | Hired for 10 hrs; Minimum of two for safety
2 | Drone pilot | Labour | 0.8 | 1250 | Day | 1000 | 25 | Hired for 10 hrs / day
[17 empty] | 366.6667 | 9.1667
[6 empty] | 420 | 10.5 |  |  |  | 2 | Field equipment / GNSS / ipad | Equipment | 3.3333 | 110 | Flat rate | 366.6667 | 9.1667
3 | Drone equipment | Equipment | 0.8 | 250 | Flat rate | 200 | 5
4 | Field equipment | Equipment | 2 | 110 | Flat rate | 220 | 5.5 |  |  |  |  | Data Acquisition |  |  |  |  | 3523.8095 | 88.0952
[11 empty] | 3 | Vehicle | Travel | 3.3333 | 150 | Flat rate | 500 | 12.5
| Miscellaneous |  |  |  |  | 2840 | 71 |  |  |  | 4 | Hotel crew | Travel | 3.3333 | 150 | Night | 500 | 12.5 | Shared room for technicians
5 | Vehicle | Travel | 3 | 150 | Flat rate | 450 | 11.25 |  |  |  | 5 | Per diem | Travel | 6.6667 | 300 | Day | 2000 | 50
6 | Hotel crew | Travel | 2 | 150 | Night | 300 | 7.5 | Shared for technicians; private for pilot |  |  | 6 | Operating costs of vehicle | Travel | 523.8095 | 1 | Km | 523.8095 | 13.0952 | 1100 km per 7 days (250 km GP-Hotel; 50 km to site)
7 | Hotel pilot | Travel | 1 | 150 | Night | 150 | 3.75
8 | Per diem | Travel | 5 | 300 | Day | 1500 | 37.5 |  |  |  |  | Processing and analysis |  |  |  |  | 2007.5 | 50.1875
9 | Operating costs of vehicle - field crew | Travel | 314.2857 | 1 | Km | 314.2857 | 7.8571 | 250 km GP-Manning; 50 km to site |  |  | 7 | Data analyst - FIXED | Labour | 1 | 1320 | Day | 1320 | 33 | Hired for 8 hrs / day; 12 hours total.
10 | Operating costs of vehicle - pilot | Travel | 125.7143 | 1 | Km | 125.7143 | 3.1429 | 250 km GP-Manning; 50 km to site |  |  | 8 | Data analyst - VARIABLE | Labour | 0.52083 | 1320 | Day | 687.5 | 17.1875
| Processing and Analysis |  |  |  |  | 8910 | 222.75
11 | Data analyst - FIXED | Labour | 5.75 | 1320 | Day | 7590 | 189.75 | Hired for 8 hrs / day; 40 hours total.
12 | Data analyst - VARIABLE | Labour | 1 | 1320 | Day | 1320 | 33
[17 empty] | 13231.3095 | 330.7827
[6 empty] | 17570 | 439.25

## 2.1. Sampling - Breakdown Struc
Breakdown structure of sampling time estimates By activity
ID |  | Project Activity Name | Estimated Effort Time Drone-assisted approach (hrs) | Estimated Effort Time Field-only approach (hrs) | Remarks
1 |  | Initial transect at a site | 1.1667 | 1.1667
2 |  | Sample time | 0 | 0 | Includes walking time.
13 |  | Total | 1.1667 | 1.1667
Measures and calculations
Preperation time was only measured once…
ID | Column1 | Task | Date | Starttime | Endtime | Total time | Remarks
1 |  | Assess suitability / layout site | 2021-08-18 | 10:13 | 11:23 | 1:10
|  | Average |  |  |  | 1:10
Average sample time was derived from time measures from the last two sampling days.
Each transect contained 10 2x2m2 quadrats
ID | Column1 | Transect | Date | Starttime | Endtime | Total time | Remarks
1 |  | T3 | 2021-08-22 | 9:48 | 11:40 | 1:52
2 |  | T4 | 2021-08-22 | 12:10 | 13:30 | 1:20
3 |  | T5 | 2021-08-22 | 14:35 | 15:25 | 0:50
4 |  | T6 | 2021-08-22 | 15:35 | 17:30 | 1:55
5 |  | T1 (invasives) | 2021-08-24 | 13:32 | 14:14 | 0:42
7 |  | T3 | 2021-08-24 | 9:23 | 10:18 | 0:55
8 |  | T4 | 2021-08-24 | 10:30 | 11:38 | 1:08
9 |  | T5 | 2021-08-24 | 11:42 | 12:35 | 0:53
|  | Average |  |  |  | 1:12

## 2.2. Drone - Breakdown Struc
Current setup is RGB collection with Phantom 4 RTK and Multispectral with RedEdge-MX
Advanced set-up is RGB collection with Zenmuse P1 and Multispectral with RedEdge-P
ID |  | Project Activity Name | Estimated Effort Time (hrs) Current set-up | Estimated Effort Time (hrs) Advanced-only approach | Estimated Effort Time (hrs) Advanced-only approach MAXIMIZED | Remarks
1 |  | (Un)packing equipment | 0.75 | 0.75 | 0.75
2 |  | Capture cal. panel reflectance | 0.25 | 0.25 | 0.25
3 |  | RGB image collection (1x 20 ha) | 3.5419 | 1.1831 | 1.1831
4 |  | Micasense image collection (1x 20 ha) | 3.6498 | 1.5068 | 1.5068
5 |  | EXTRA: RGB image collection (1x 5 ha) | 0 | 0 | 0.29577
6 |  | EXTRA: Micasense image collection (1x 5 ha) | 0 | 0 | 0.37669
|  | Total hours | 8.1918 | 3.6898 | 4.3623
|  | Total hours of site pair | 16.3835 | 6.6297 | 7.9746
|  | Work days of site pair | 2 | 0.8 | 1
|  | Total hectares | 40 | 40 | 50
Calculated difference in time (minutes) per hectare between measured and estimated data collection time
… which was used to correct time estimates with an advanced sensor setup
ID |  | Name | Resolution (cm) | Area (ha) | Overlap | Start time | End time | Duration (min) | Actual time per ha | Estimated duration | Estimated time per ha | % Difference estimated-actual time | Estimated duration (advanced sensors) | Estimated Time per ha (advanced sensors) | Estimated Differece per ha, accounted for difference (advanced sensors)
1 |  | RGB - Wildfire Little Smoky (Flight Zenmuse - main) | 1.5 | 13.2646 | 90/85 | 2021-08-19 14:25 | 2021-08-19 16:09 | 103.5333 | 7.8052 | 91 | 6.8604 | 13.7729 | 21 | 1.5832 | 2.8982
2 |  | RGB - Wildfire Chin A (Manning 2018 - Flight Zenmuse - main) | 1.4 | 13.2371 | 90/85 | 2021-08-22 10:02 | 2021-08-22 12:41 | 159.45 | 12.0457 | 117 | 8.8388 | 36.2821 | 23 | 1.7375 | 3.1808
3 |  | RGB - Wildfire Chin A (Manning 2018 - Flight Phantom 4 - gap) | 1.4 | 5.9641 | 90/85 | 2021-08-22 15:14 | 2021-08-22 16:17 | 63.3167 | 10.6163 | 20 | 3.3534 | 216.5833 | 12 | 2.012 | 3.6834
4 |  | RGB - Wildfire Chin B (Manning 2019 - Flight Phantom 4) | 1.5 | 3.3026 | 90/85 | 2021-08-23 11:26 | 2021-08-23 12:06 | 39.75 | 12.0359 | 24 | 7.267 | 65.625 | 8 | 2.4223 | 4.4344
|  | Average | [6 empty] | 10.6258 |  | 6.5799 | 83.0658 |  | 1.9388 | 3.5492
5 |  | Multispec - Wildfire Little Smoky (GrandeCache - Flight Micasense 2) | 2.9 | 10.6271 | 80/80 | 2021-08-25 18:45 | 2021-08-25 19:56 | 71.0833 | 6.6889 | 54 | 5.0813 | 31.6358 | 21 | 1.9761 | 3.0032
6 |  | Multispec - Wildfire Chin A (Manning 2018 - Flight Micasense) | 3 | 9.6084 | 80/80 | 2021-08-21 20:52 | 2021-08-21 21:55 | 63.7667 | 6.6366 | 44 | 4.5793 | 44.9242 | 19 | 1.9774 | 3.0053
7 |  | Multispec - Wildfire Chin B (Manning 2019 - Flight Micasense - missed transect) | 2.2 | 1.8201 | 80/80 | 2021-08-23 22:17 | 2021-08-23 22:42 | 24.6 | 13.5155 | 18 | 9.8894 | 36.6667 | 8 | 4.3953 | 6.6799
8 |  | Multispec - Wildfire Chin B (Manning 2019 - Flight Micasense - main) | 2.2 | 3.1 | 80/80 | 2021-08-23 19:00 | 2021-08-23 19:52 | 52.5667 | 16.957 | 27 | 8.7097 | 94.6914 | 11 | 3.5484 | 5.3928
|  | Average | [6 empty] | 10.9495 |  | 7.0649 | 51.9795 |  | 2.9743 | 4.5203

## 2.3. Processing - Breakdown
For single site pair (40 ha total)
ID | Column1 | Project Activity Name | Estimated Effort Time (hrs) Drone-assisted approach FIXED | Estimated Effort Time (hrs) Drone-assisted approach VARIABLE | Estimated Effort Time (hrs) Field-only approach FIXED | Estimated Effort Time (hrs) Field-only approach VARIABLE | Remarks
1 |  | Quality check of field-data | 2 | 2 | 2 | 1
2 |  | Photogrammetric processing | 4 | 1.5 | 0 | 0 | None of the estimates include "waiting" times
3 |  | Data pre-processing | 4 | 1.5 | 0 | 0
4 |  | Creating vegetation structure maps | 12 | 0 | 0 | 0
5 |  | Creating plant function types maps | 12 | 0 | 0 | 0
6 |  | Site summaries / comparisons | 8 | 2 | 4 | 1
7 |  | Data management | 4 | 0.5 | 2 | 0.25
8 |  | Contingency time | 0 | 0.5 | 0 | 0.25 | To account for errors and unforseen activities
|  | Total hours | 46 | 8 | 8 | 2.5
|  | Total work days | 5.75 | 1 | 1 | 0.3125